## Process overview
POST
LAUNCH REVIEW
DISCOVERY
GATE
1
STAGE 2:
Design
GATE
2
STAGE 3/4:
Commercialise/
Production
GATE
3
STAGE 5:
Launch

## Who Does What
Stage & Gate Areas of Responsibility
| STAGE GATE RACI: | R = Responsible A = Accountable C = Consulted I = Informed
|  | PROJECT LEAD | R&D | CATEGORY | SALES | FINANCE | PROCUREMENT | MARKETING | QA | LOGISTICS & DEMAND PLANNING | SUPPLY PLANNING | OPS
STAGE 1: IDEATION | KEY TASKS
| Category Planning/deep dives | C |  | RA | C | i | I | C | C | C | I
| Ideation/ Innovation Workshops | RA | C | [8 empty] | I | bar: RA to I
| Market Research on customer and category | I | bar: RA to I
| Customer feedback/ Insights (JCP/ strategy sessions) | I |  | RA | C |  |  | C | I | I | I | I
| Concept Prep & Research | I | I | [8 empty] | I | bar: RA to I
| Concept test/internal Research | A | I | bar: RA to I
| Project kick off | RA | C | [8 empty] | C | bar: RA to I
| Draft Gate 1 Paper | RA | C | [8 empty] | I | bar: RA to I
| Strategic fit, consumer and customer opportunity | C | C | bar: RA to I
| Submit Paper for approval | RA | I | [8 empty] | I | bar: RA to I
| Assign project number post 'GO' | RA
| Assign as official live project | RA
Gate 1: Does the idea/s generated appear to meet the needs of the market andbusiness and warrant deeper investigation?
STAGE 2: DESIGN | KEY TASKS
| Product Development Brief Issued | C | I | C | C | I | I | RA | 1 |  |  | I
| Project Timeline complete | RA | [9 empty] | I | bar: RA to I
| Concept Artwork Development and research validation | C | bar: RA to I
| Review new ingredient PIFs (where applicable) | RA | I | bar: RA to I
| Review potential health or ingredient claims | R | bar: RA to I
| Customer Engagement | I |  | RA: 1; C: RA; C: I
| Initial COG's, Volume assumptions, Ranging, and RRP | C |  | I | C | C | I | RA |  | I
| CAPEX assessment | I | [9 empty] | RA | bar: RA to I
| In Bakery Trials (incl. trial form prep) | RA | C | [8 empty] | C | bar: RA to I
| Recipe Signoff (sensory evaluation) | C | C | [8 empty] | I | bar: RA to I
| Submit Gate 2 paper for approval | RA | [9 empty] | C | bar: RA to I
Gate 2: Is the product and business case sound?
STAGE 3: COMMERCIALISE | KEY TASKS
| Bakery Commercial Trials completed | RA | bar: RA to I
| Approved ingredient or health claims | A | bar: RA to I
| Technical assessment complete | C | bar: RA to I
| Market attractiveness complete | I | bar: RA to I
| Customer engagement, volumes and financials | I |  | C | RA | C | I | C
| Artwork Development Commences | C | C | bar: RA to I
| Input packaging costs into the Costing (new formats) | RA | bar: RA to I
| All product, packaging and packing quotes received | RA |  | I: C; C: R; I: I
| Input COGs, product and quote information into the New Line Summary | I | bar: RA to I
| Input volume, distribution, range type, sell & shelf price into the New Line Summary | I |  | C | C | I | I | RA
| Input Category Performance into the New Line Summary & review financial information | I | bar: RA to I
| Masterdata form to be completed | RA | bar: RA to I
| UBF/GS1 form completed | C | bar: RA to I
| Master Data set up in - BOM completed | C | C |  |  | RA | C | C | C |  | I
| Product pack mock ups completed | I | bar: RA to I
Trade Activation & Launch Plan agreed | bar: RA to I
| Customer Presentations complete | C |  | RA: C; C: RA; i: I; C: C
Marketing plan agreed | bar: RA to I
| Submit Gate 3 for approval | RA | [9 empty] | C | bar: RA to I
Gate 3: Is everything in place for launch?
STAGE 4: LAUNCH | KEY TASKS
| Forecast & final pricing provided | I |  | C | RA | C | C | C |  | R | C | C
| Production Scheduled | I |  |  | C | C | C |  |  | I | RA
| Packaging orders placed | I | bar: RA to I
| Unique material orders placed | C |  | i: C; I: RA; I: I
| Artwork Development complete | I |  |  |  |  | I | RA | C | C | C | C
| Packaging printed | I | [9 empty] | I | bar: RA to I
| Batch/Job sheets for Bakery | C | [9 empty] | I | bar: RA to I
| QAS sheets | A | [9 empty] | I | bar: RA to I
| First Production Complete | C | [9 empty] | RA | bar: RA to I
| First Production review | RA | C | [8 empty] | C | bar: RA to I
| Final GS1 reports requested & received | I |  | RA: I; C: I; C: A; C: R
| Product Images loaded to Sku Library | I |  | C: I; C: A; C: R
| Customer orders placed | I | [9 empty] | I | bar: RA to I
| Post Launch Reviews - 1 week on shelf, 4wks,12wks, 6mths, 12mths | R | C | [8 empty] | C | bar: RA to I

## Gate 1
The intent of this document is to review ideas from the ideation phase, so that they are assessed for fit to strategy, broad feasibility and link to external trend or insight. Lack of information at this point is not a reason to kill an idea. If the idea warrants a re-think on strategy due to the nature of the opportunity, please flag this in the background.
Project Name | Idea Generator: |  | Who's responsible for input to template
Summary Description
Category |  | Project Type
Portfolio
Date Project Approved |  | Project Number
1. Background |  |  | Marketing/PD
2. Project Scope / Idea |  |  | Marketing/PD
3. Can we manufacture with current capabiility/should we outsource? |  |  | PD
4. Target Date for Gate 1 Approval: |  |  | Marketing/PD
Target Project milestones: Product Brief Bench 1 Bench 2 Bench 3 Final Benchtop Samples & Costs Trial x 1 Final Financials Range Review Presentation On shelf date
Sign off:
IDEATION - Initial Idea Fit to Strategy
Decision - Go / Stop / Recyle / Hold

## Gate 2
Your score |  |  |  | Final Score
The intent of this document is to record our estimates, and highlight what we know , what we don't know and cost of filling those knowledge gaps. Be candid about your estimates. It is expected we are at +/- 50% at this gate. Do not feel badly about acknowledging a knowledge gap. Focus on what it will take to fill this gap.
Project Name |  |  | Project Manager |  |  | Who's reponsible for input to template
Summary Description
Category |  |  | Project Type
Portfolio
Channel
Date of Gate Approval |  |  | Project Number
1. Project Summary | [6 empty] | Key questions and content to include
1.1 Background | [5 empty] | Marketing | Why is this project important - include consumer insight and customer understanding, trends, fit to strategy, main customer and consumer pain points to be addressed by this product (s)
1.2 Refined Project Scope /Concept | [5 empty] | Marketing | Tighter understanding of flavours being explored, protype and concept statement that summarises the idea Current capability to produce or outsource recommended?
1.3 Customer Interest / Considerations | [5 empty] | Sales | Why would the Customer be interested in this product, have they been engaged at this early stage?
2.0 Consumer/Customer/Category Appeal
2.1 Consumer Attractiveness | [5 empty] | Marketing | Do we have any onsumer understanding or indication of consumer appeal or attractiveness?
2.2 Customer/Category Attractiveness | [5 empty] | Sales | Customer feedback. What is the market attractiveness, growth, category performance and how will this drive customer growth
3.0 Business Impact
Congruence to Strategy | [5 empty] | Marketing | Is this a Strong Fit?
Impact to Strategy | [5 empty] | Marketing | Does it deliver to business growth goals and strategic intent?
4. Key Objectives & Financial Goals | [5 empty] | Marketing & Sales | Objective re alignment to strategy (non financial) Units per store per week target Annual NSV & Fiscal Year Annual & Fiscal Year Commercial Margin ($ & %)
4.1 Financial Assumptions
Total Annual Volume (Units) Anticipated Distribution by Account (by SKU) Note: Key assumptions below in separate table | [5 empty] | Marketing & Sales | What is the anticipated volume for the sku's, including key assumptions
Units per store per week: 12 weeks 6 months 12 months (Combine baseline and promo average) List assumptions) | [5 empty] | Marketing & Sales | Target, including assumptions
Target RRP | [5 empty] | Marketing & Sales | Recommend retail pricing
Estimated Product COG's per unit | [5 empty] | Finance | Prepare draft P&L to understand to cost of goods for the product
Key product cost assumptions | [5 empty] | Finance | Include any new or unique ingredients that may impact COG's, cost assumptions made
Project Costs (includes trial costs, research, sensory evaluation) | [5 empty] | R&D | Trial Costs: Estimated total trial costs are $?K of which $?K recoverable and $?K unrecoverable. Sensory Validation Costs: Internal screening
Cannibalisation | [5 empty] | Commercial | Provide hypothesisied negative impact launch of this product could have on other products
Capital | [5 empty] | Ops | What capital is required and at what cost
Launch Markets | [5 empty] | Sales | Test Market, National, Export
Dist'n Channels | [5 empty] | Sales | Key channels to sell product in - ie modern trade, traditional trade
5.0 Target Dates | [5 empty] | Project Lead
Approved prototype |  | Date
Recipe Sign off |  | Date
Target trial date |  | Date
Gate 2 Approval |  | Date
Does this project need to be Fast tracked? | Yes/No
6.0 Project Team | [5 empty] | Project Lead
Function |  | Name |  |  | Estimate of Resource Commitment
Marketing |  |  |  |  | Med
Innovation |  |  |  |  | High
Supply Planning |  |  |  |  | Low
Packaging |  |  |  |  | Low
Product Development |  |  |  |  | Med
Procurement |  |  |  |  | Med
Finance |  |  |  |  | Low
Production |  |  |  |  | High
Sales |  |  |  |  | Med
Logistics |  |  |  |  | Med
Signed off:
Gate 2: DESIGN - Concept development
Decision - Go / Stop / Rcycle / Hold
Project #

## Gate 3
Your score | [7 empty] | Final Score
The intent of this document is to assist with the decision to invest heavily in development ready for launch. Key focus is on the size of the prize and our confidence in our ability to win. Any business costs to develop the product such as capital requirements, artwork, packaging, unique ingredients and supply, or costs to complete trials should be highlighted.
Project Name | [6 empty] | Project Manager |  |  |  |  | Who's reponsible for input to template
Summary Description
Category | [6 empty] | Project Type
Portfolio
Channel
Date of decision |  |  | TBC |  |  |  | Project Number
1. Background | [12 empty] | Key Questions and content to include
Refined Project Scope / Idea (If any changes) | [11 empty] | Marketing
Technical Summary | [11 empty] | Ops, Procurement, QA | Are there any issues identified from operations / procurement / QA with this project that needs highlighting.
2. Consumer/Customer Fit
Consumer Attractiveness | [11 empty] | Marketing
Customer/Category Attractiveness | [11 empty] | Marketing
3.0 Business Impact
Congruence to Strategy | [11 empty] | Marketing | Bring forward from Gate 2 Development Paper
Impact to Strategy | [11 empty] | Marketing
What are the business consequences of not carrying out the project, if any? | [11 empty] | Marketing
4. Key Objectives and Financial Goals | [11 empty] | Sales/Finance | Objective re alignment to strategy (non financial) Units per store per week target Annual NSV & Fiscal Year Annual & Fiscal Year Commercial Margin ($ & %)
PLEASE NOTE: FINANCIALS & VOLUME PURELY INDICATIVE PRIOR TO UNDERSTANDING RETAILER RANGING OR DISTRIBUTION. NOT TO BE USED AS FORECAST. REFINED VOLUME & FINANCIALS AVAILABLE IN LATE FEB AND BEYOND.
4.1 Indicative Financials ($'000) |  |  |  | Absolute |  |  |  | Incremental
|  |  |  | FY23 |  | FY24 | FY25 | FY23 |  | FY24 | FY25
| Cartons | Units
Volume (Units) | [11 empty] | Sales
NSV
COGs
A&P (15% of NSV)
Commercial Margin
CM %
Capital: | [5 empty] | 0
Development Costs | [5 empty] | 0
Non - Recoverable costs | [5 empty] | 0
Recoverable costs | [5 empty] | 0
Implementation Costs | [5 empty] | 0
Key Project costs
Prototyping/development costs
Full Trial costs | [5 empty] | 0
Raw Materials | [5 empty] | 0
Artwork/plates | [5 empty] | 0
Legal | [5 empty] | 0
Capital | [5 empty] | 0
Tooling | [5 empty] | 0
Other | [5 empty] | 0
4.2 Financial Assumptions |  |  |  | N.A. - productivity
|  |  |  | New product |  |  |  | Reference product
|  |  |  | Name of new product |  |  |  | Name of reference product
Volume |  |  |  | Units/Store |  |  |  | Units/Store
Cannibalisation |  |  |  | % |  |  |  | %
Product Size |  |  |  | no of g |  |  |  | no of g
Shelf Price |  |  |  | $ / unit |  |  |  | $ / unit
Retailer Margin |  |  |  | % |  |  |  | %
Trade Spend |  |  |  | $ |  |  |  | $
Product Cost |  |  |  | $/kg |  |  |  | $/kg
A&P Incremental |  |  |  | $ ,(000) |  |  |  | $ ,(000)
Launch Markets |  |  |  | Domestic
Distribution Channels |  |  |  | Grocery
Site of Manufacture |  |  |  | Noble Park North
5. Marketing Strategy
Communication Strategy
Pricing Strategy
6. Project Budget
6.1 Project Budget - Costs to Proceed - Development only (prior to taking launch decision)
Development required |  |  |  | Description | [5 empty] | Amount $k | Budgeted (Y/N)
Packaging
Research
Trials
Legal
Allergen testing
Materials
CAPEX
Travel
Other'
Other'
TOTAL COSTS AT RISK
Estimated Recoveralble Cost
Estimated Unrecoverable Cost
6.2 Estimated Launch Costs
Implementation costs |  |  |  | Description | [5 empty] | Amount | Budgeted (Y/N)
CAPEX
Launch materials
Advertising
Artwork
Pre-press
Finished goods write off
Materials write off
Other
TOTAL
7.0. Target Dates:
Planogram in store/Launch date:
Target Gate 3 date:
Other key dates: eg trade shows, samples required
8. Product codes
SKU 1 |  |  |  | List details of SKU
SKU 2
SKU 3
SKU 4
SKU 5
9. Constraints |  |  |  | Nil
10. Business & Technical Risks
11.1 Project Team
Function |  |  |  |  | Name |  |  |  | Estimate of Resource Commitment
Marketing
Supply Planning
Packaging
R&D
Business Development
Engineering
Procurement
Finance
Production
Sales
Logistics
What are the business consequences of not carrying out the project, if any?
Signed Off:
PROJECT PLAN
Sponsor & NAR approval; if A then INAR
Cat Tem & ELT Approval
PROJECT PLAN
Sponsor & NAR approval; if A then INAR
Cat Tem & ELT Approval
Decision - Go / Kill / Redirect
Gate 3: COMMERCIALISE
Project #
Jim to prepare by SKU

## G 3 P&L (hidden)
Financial Summary
My 1st Veg (100g)
[5 empty] | Cannibalised |  |  | Incremental to
Launch Date: April 2009 |  | My 1st Veg (100g) |  |  | Veg (145g 30%/400g 70%) |  |  | Current Business |  |  |  | B/(W)
|  | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 | 2008 OB | 2008 OB
Retail / Distributor Price |  | 2.99 | 2.99 | 2.99 | 0 | 0 | 0 |  |  |  | 2.31
Retail / Distributor Margin (exc terms) |  | 19.95% | 19.95% | 19.95% | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 2.596%
Retail / Distributor Margin (inc terms) |  | 27.65% | 27.65% | 27.65% | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | 0%
Volume (Tons) |  | 191 | 228 | 240 | 133.7 | 159.6 | 168 | 57.3 | 68.4 | 72 | 0 | 191
Gross Operating Revenue |  | 4131.7853 | 4932.1836 | 5191.7722 | 1914.696 | 2285.6058 | 2405.9008 | 2217.0893 | 2646.5778 | 2785.8714 | 0 | 4131.7853
per kg |  | 21.6324 | 21.6324 | 21.6324 | 14.3208 | 14.3208 | 14.3208 |  |  |  | 8.5445
Case Deals |  | 0 | 0 | 0 | 70.8438 | 84.5674 | 89.0183 | -70.8438 | -84.5674 | -89.0183 | 0 | 0
per kg |  | 0 | 0 | 0 | 0.52987 | 0.52987 | 0.52987 |  |  |  | #DIV/0!
% to OR Gross |  | 0% | 0% | 0% | 3.7% | 3.7% | 3.7% |  |  |  | 13.3%
Net Revenue (NR) |  | 4131.7853 | 4932.1836 | 5191.7722 | 1843.8523 | 2201.0383 | 2316.8825 | 2287.9331 | 2731.1452 | 2874.8897 | 0 | 4131.7853
per kg |  | 21.6324 | 21.6324 | 21.6324 | 13.791 | 13.791 | 13.791 |  |  |  | #DIV/0!
Cost of Sales - Variable |  | 1850.79 | 2209.32 | 2325.6 | 699.251 | 834.708 | 878.64 | 1151.539 | 1374.612 | 1446.96 | 0 | -1850.79
per kg |  | 9.69 | 9.69 | 9.69 | 5.23 | 5.23 | 5.23 |  |  |  | 3.3332
Available Profit (AP) exc FME |  | 2280.9953 | 2722.8636 | 2866.1722 | 1144.6013 | 1366.3303 | 1438.2425 | 1136.3941 | 1356.5332 | 1427.9297 | 0 | 2280.9953
per kg |  | 11.9424 | 11.9424 | 11.9424 | 8.561 | 8.561 | 8.561 |  |  |  | #DIV/0!
% to NR |  | 55.21% | 55.21% | 55.21% | 62.08% | 62.08% | 62.08% |  |  |  | #DIV/0!
Cost of Sales - FME |  | 194.82 | 232.56 | 244.8 | 137.711 | 164.388 | 173.04 | 0 | 0 | 0 | 0 | 0
per kg |  | 1.02 | 1.02 | 1.02 | 1.03 | 1.03 | 1.03 |  |  |  | 0.54972
Available Profit (AP) |  | 2086.1753 | 2490.3036 | 2621.3722 | 1006.8903 | 1201.9423 | 1265.2025 | 1136.3941 | 1356.5332 | 1427.9297 | 0 | 2280.9953
per kg |  | 10.9224 | 10.9224 | 10.9224 | 7.531 | 7.531 | 7.531 |  |  |  | #DIV/0!
% to NR |  | 50.49% | 50.49% | 50.49% | 54.61% | 54.61% | 54.61% |  |  |  | #DIV/0!
A&C |  | 314.0157 | 374.846 | 394.5747 | 140.1328 | 167.2789 | 176.0831 | 0 | 0 | 0 | 0 | 0
per kg |  | 1.6441 | 1.6441 | 1.6441 | 1.0481 | 1.0481 | 1.0481 |  |  |  | #DIV/0!
% to NR |  | 7.6% | 7.6% | 7.6% | 7.6% | 7.6% | 7.6% |  |  |  | #DIV/0!
Net Contribution |  | 1772.1597 | 2115.4576 | 2226.7975 | 866.7575 | 1034.6634 | 1089.1194 | 1136.3941 | 1356.5332 | 1427.9297 | 0 | 2280.9953
per kg |  | 9.2783 | 9.2783 | 9.2783 | 6.4829 | 6.4829 | 6.4829 |  |  |  | #DIV/0!
% to NR |  | 42.89% | 42.89% | 42.89% | 47.01% | 47.01% | 47.01% |  |  |  | #DIV/0!
Overheads |  | 392.5196 | 468.5574 | 493.2184 | 175.166 | 209.0986 | 220.1038 | 0 | 0 | 0 | 0 | 0
per kg |  | 2.0551 | 2.0551 | 2.0551 | 1.3101 | 1.3101 | 1.3101 |  |  |  | #DIV/0!
% to NR |  | 9.5% | 9.5% | 9.5% | 9.5% | 9.5% | 9.5% |  |  |  | 11.9%
Operating Income (OI) |  | 1379.6401 | 1646.9002 | 1733.5791 | 691.5916 | 825.5648 | 869.0156 | 1136.3941 | 1356.5332 | 1427.9297 | 0 | 2280.9953
per kg |  | 7.2232 | 7.2232 | 7.2232 | 5.1727 | 5.1727 | 5.1727 |  |  |  | #DIV/0!
% to NR |  | 33.39% | 33.39% | 33.39% | 37.51% | 37.51% | 37.51% |  |  |  | #DIV/0!
Assumptions
Cannibalisation 70% (30% tube / 70% 150g)
Working Section: (all input in shaded areas only)
|  |  | My 1st Veg (100g) |  |  | Veg (145g 30%/400g 70%)
Volume (Tons) |  | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 |  |  |  | 2008 OB
|  | 191 | 228 | 240 | 133.7 | 159.6 | 168 |  |  |  | 0
Cannibalisation | 70%
Cannibalised
|  |  | My 1st Veg (100g) |  |  | Veg (145g 30%/400g 70%)
Retail / Distributor Price (Inc GST) |  | 2.99 | 2.99 | 2.99 | 0 | 0 | 0 |  |  |  | 2.31
GST |  | 0% | 0% | 0% | 0% | 0% | 0% |  | GST Products |  | 0%
Confectionery
Retail / Distributor Price (Exc GST) |  | 2.99 | 2.99 | 2.99 | 0 | 0 | 0 |  | Snackabouts |  | 2.31
Retail / Distributor Margin (exc terms) |  | 19.95% | 19.95% | 19.95% | #DIV/0! | #DIV/0! | #DIV/0! |  | Tang |  | 2.596%
Retail / Distributor Margin (inc terms) |  | 27.65% | 27.65% | 27.65% | #DIV/0! | #DIV/0! | #DIV/0! |  | Biscuits |  | 11.97%
Unit Weight (grams) |  | 100 | 100 | 100 | 1000 | 1000 | 1000 |  |  |  | 238
Units / carton |  | 15 | 15 | 15 | 1 | 1 | 1 |  |  |  | 12
Weight / carton |  | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 |  |  |  | 2.856
B1 Price / ctn |  | 43.3 | 43.3 | 43.3 | 19.11 | 19.11 | 19.11 |  |  |  | 33.29
Order Quantity |  | 13.5% | 13.5% | 13.5% | 13.5% | 13.5% | 13.5% |  |  |  | 13.5%
Warehouse Allowance |  | 4% | 4% | 4% | 4% | 4% | 4% |  |  |  | 6%
Ullage |  | 0.15% | 0.15% | 0.15% | 0.15% | 0.15% | 0.15% |  |  |  | 0.25%
Net Price / ctn |  | 35.9024 | 35.9024 | 35.9024 | 15.8451 | 15.8451 | 15.8451 |  |  |  | 2700%
Other Allowances (eg distress) |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
Rebates |  | 9.62% | 9.62% | 9.62% | 9.62% | 9.62% | 9.62% |  |  |  | 9.62%
Gross Operating Revenue / ctn |  | 32.4486 | 32.4486 | 32.4486 | 14.3208 | 14.3208 | 14.3208 |  |  |  | 2440%
Case Deals |  | 0% | 0% | 0% | 3.7% | 3.7% | 3.7% |  |  |  | 13.3%
Cost of Sales / ctn
Raw Materials |  | 4.86 | 4.86 | 4.86 | 2.88 | 2.88 | 2.88 |  |  |  | 5.85
Packaging |  | 5.34 | 5.34 | 5.34 | 1.32 | 1.32 | 1.32 |  |  |  | 2.02
Labour |  | 0.045 | 0.045 | 0.045 | 0.1 | 0.1 | 0.1 |  |  |  | 0.82
VME |  | 3.525 | 3.525 | 3.525 | 0.6 | 0.6 | 0.6 |  |  |  | 0.54
FME |  | 1.53 | 1.53 | 1.53 | 1.03 | 1.03 | 1.03 |  |  |  | 1.57
Productivity |  | 0.27 | 0.27 | 0.27 | 0 | 0 | 0 |  |  |  | -0.71
Co-Packer / Other |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | 15.57 | 15.57 | 15.57 | 5.93 | 5.93 | 5.93 | 2009 | 2010 | 2011 | 10.09
Cost of Sales / kg | [7 empty] | b/(w) | b/(w) | b/(w)
Raw Materials |  | 3.24 | 3.24 | 3.24 | 2.88 | 2.88 | 2.88 | -0.36 | -0.36 | -0.36 | 2.0483
Packaging |  | 3.56 | 3.56 | 3.56 | 1.32 | 1.32 | 1.32 | -2.24 | -2.24 | -2.24 | 0.70728
Labour |  | 0.03 | 0.03 | 0.03 | 0.1 | 0.1 | 0.1 | 0.07 | 0.07 | 0.07 | 0.28711
VME |  | 2.35 | 2.35 | 2.35 | 0.6 | 0.6 | 0.6 | -1.75 | -1.75 | -1.75 | 0.18908
FME |  | 1.02 | 1.02 | 1.02 | 1.03 | 1.03 | 1.03 | 0.01 | 0.01 | 0.01 | 0.54972
loss factor on blend 4.58 -> 4.76 |  | 0.18 | 0.18 | 0.18 | 0 | 0 | 0 | -0.18 | -0.18 | -0.18 | -0.2486
Co-Packer / Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10.38 | 10.38 | 10.38 | 5.93 | 5.93 | 5.93 | -4.45 | -4.45 | -4.45 | 3.5329
Freight & Warehouse / kg |  | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 |  |  |  | 0.35
Raw Mat and Pack'g Write off / kg |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | 10.71 | 10.71 | 10.71 | 6.26 | 6.26 | 6.26 |  |  |  | 3.8829
Advertising (Option 1)
Advertising % to OR |  | 7.6% | 7.6% | 7.6% | 7.6% | 7.6% | 7.6% |  |  |  | 4%
Advertising (Option 2) |  | Only one option can be used. The other must be blank.
Absolute ('000) |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Incremental Advertising ('000) |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Overheads
Overheads % to OR |  | 9.5% | 9.5% | 9.5% | 9.5% | 9.5% | 9.5% |  |  |  | 11.9%
Pack Design - New Products ('000) |  | 0 | 0 | 0
Incremental Overheads ('000) |  | 0 | 0 | 0

## Gate 4
Your score |  |  |  |  | Final Score
The intent of this document is to confirm that the product is ready for commercial launch. Emphasis is on ensuring Manufacturing have approved the process for full scale production and that costs have been finalised and meet original financial objectives. This is where we will reconfirm that we have met our original NPD brief and delivered on the intended consumer benefits. Any major risks to success must be highlighted at this point and we must ask ourselves is there any reason not to proceed?
Project Name |  |  |  | Project Manager |  |  |  |  | Who's reponsible for input to template
Summary Description
Category |  |  |  | Project Type
Portfolio
Channel
Date of decision |  |  |  | Project Number
1. Project Summary | [9 empty] | Key Questions and content to include
1. Background | [8 empty] | Marketing | Bring forward background from idea ilter and add in additional consumer insight and customer understanding, trends, fit to strategy, main customer and consumer pain points to be addressed by this product (s)
1.2 Refined Project Scope /Concept (If any changes) | [8 empty] | Marketing/PD | Tighter understanding of flavours being explored, protype and concept statement that summarises the idea
1.3 Technical Summary | [8 empty] | PD | Have we delivered the product to the design brief, any issues from the trial (if so what and what corrective action was taken).
2. Consumer/Customer Fit
Consumer Attractiveness | [8 empty] | Marketing | Tested or hypothesisied. Bring frward from Feasibility if no change
Market Attractiveness | [8 empty] | Marketing | Market size and growth, our right to win and who our competitors are. Bring forward from Feasibility if no change.
Customer Interest/considerations | [8 empty] | Commercial | Has the trade accepted the product, do wehave confirmed ranging. If not when is it expected
3. Key Objectives and Financial Goals | [8 empty] | Commercial | Objective re alignment to strategy (non financial) Units per store per week target Annual NSV & Fiscal Year Annual & Fiscal Year Commercial Margin ($ & %) Bring forward from Feasibility if no change
3.1 Financials ($'000) | Absolute |  |  |  | Incremental - Based on assumed cannibalisation |  |  |  | Sales
| FY23 |  | FY24 | FY25 | FY23 |  | FY24 | FY25
Volume (Units)
NSV
Commercial Margin
A&P
3.2 Financial Assumptions | New product |  |  |  | Reference product |  |  |  | Sales
Product Name | Name of new product |  |  |  | Name of reference product
Volume | Units |  |  |  | Units
Assumed Cannibalisation | % |  |  |  | %
Product Size | no of g |  |  |  | no of g
Shelf Price | $ / unit |  |  |  | $ / unit
Retailer Margin (by Account) | % |  |  |  | %
Trade Spend | %/$ |  |  |  | %/$
Product Cost | COG's by unit |  |  |  | COG's by unit
Marketing $ | $ ,(000) |  |  |  | $ ,(000)
Launch Markets | Domestic/Export
Distribution Channels | Grocery, Foodservice, Airlines, Contract
4. Project Budget | [8 empty] | Project Lead
4.1 Project Budget - Costs to Proceed - Development only (prior to taking launch decision)
Development required | Description | [5 empty] | Amount | Budgeted (Y/N)
Packaging
Research
Trials
Materials
CAPEX
Other'
Other'
Other'
TOTAL COSTS AT RISK
Estimated Recoveralble Cost
Estimated Unrecoverable Cost
4.2 Estimated Launch Costs | [8 empty] | Marketing
Implementation costs | Description | [5 empty] | Amount | Budgeted (Y/N)
CAPEX | Text
Launch materials
Advertising
Artwork
Pre-press
Finished goods write off
Materials write off
Other
TOTAL | [6 empty] | 0
5. Marketing & Sales Strategy | [8 empty] | Marketing
Communication Strategy (launch Plan) | Include images if available for creative to bring the plan to life
Pricing Strategy | [8 empty] | Sales
Distribution Strategy | [8 empty] | Sales
6. Supply Considerations (summary) | [8 empty] | Demand Planning
7.0 What are the business consequences of not carrying out the project, if any? | [8 empty] | Marketing
8.0. Target Dates: | [8 empty] | Project Leader
Target launch date:
Target Post Launch Review Dates:
Other key dates:
9. Product codes | [8 empty] | Finance
SKU 1
SKU 2
SKU 3
SKU 4
10. Constraints
11. Business & Technical Risks | [8 empty] | Mkt/Ops/QA
12.1 Project Team | [8 empty] | Project Lead
Function |  | Name |  |  |  | Estimate of Resource Commitment
Marketing
Supply Planning
Packaging
R&D
Business Development
Engineering
Procurement
Finance
Production
Cat devlpt/sales
Logistics
Signed off:
PROJECT PLAN
Sponsor & NAR approval; if A then INAR
Cat Tem & ELT Approval
Gate 4: LAUNCH PLAN - Sales, Marketing, Financials
Decision - Go / Stop / Hold / Recycle

## 1 & 3 month review
Project Name
Project Number
Project Type | New Product
Channel | Grocery
Launch Date | DC Date
2021-08-25
Flavour/SKU | Column1 | SKU 1 | SKU 2 | SKU 3 | Who's responsible for input of data and commentary | On track/Off Track | Here are the BBB financials (Demand Forecast) for FY22:
Metrics vs. PD Brief (and Gate Paper) | [6 empty] | Until advised otherwise by WOW, distribution has been assumed the same for all 3 variants, so volume (cartons) and revenue are same.
DIFOT | Plan
Actual
Distribution | Plan
Actual
Volume | Plan
Actual
UPSPW | Plan
Actual
RSP | Plan
Actual
COGS | Plan
Actual
% Gross Margin | Plan
Actual
% Contribution Margin | Plan
Actual
Consumer feedback
Key Project Learnings: | Please comment on successes and points to improve
Speed to Market | Project team
Consumer feedback
Customer feedback
Project Team | How effective was the team, dynamics, input, speed, ownership of functional area. What could we do differently, better?
PD - Development
Production
Packaging
Product
Any future changes to the product
Product supply - forecasting accuracy
Communication
Pricing compliance
Reviewed by:
POST LAUNCH EVALUATION:

## 6 & 12 months launch review
Project Name
Project Number
Project Type | New Product
Channel | Grocery
Launch Date | DC Date
2021-08-25
Flavour/SKU | Column1 | SKU 1 | SKU 2 | SKU 3 | SKU 4 | SKU 5 | SKU 6 | Who's responsible for input of data and commentary | On track/Off Track | Here are the BBB financials (Demand Forecast) for FY22:
Metrics vs. PD Brief (and Gate Paper) | [9 empty] | Until advised otherwise by WOW, distribution has been assumed the same for all 3 variants, so volume (cartons) and revenue are same.
12 months | Review Date
DIFOT | Plan
Actual
Distribution | Plan
Actual
Volume | Plan
Actual
UPSPW | Plan
Actual
RSP | Plan
Actual
COGS | Plan
Actual
% Gross Margin | Plan
Actual
% Contribution Margin | Plan
Actual
Consumer feedback
Other
Launch Date | Plan
Actual
Full Year Volume Forcast | Plan
Actual
Launch Costs $ | Plan
Actual
Development costs $ | Plan
Actual
Key Project Learnings: | Please comment on successes and points to improve
Speed to Market | Project team
Consumer feedback
Customer feedback
Project Team | How effective was the team, dynamics, input, speed, ownership of functional area. What could we do differently, better?
PD - Development
Production
Packaging
Product
Any future changes to the product
Product supply - forecasting accuracy
Communication
Pricing compliance
Reviewed by:
POST LAUNCH EVALUATION:

## Sensory Evaluation
Session Date |  | Project | Name
Please write any comments you may have for the sensory attributes listed in the boxes below, then using the scale above, give each of the samples an overall rating. Once you have completed the evaluation rate each of the samples in order of the preference
Product | Key Ingredients (Differences between samples) | Appearance | Texture | Flavour | Next Steps
SAMPLE SENSORY EVALUATION

## Scoring Criteria
KEY QUESTION: Is the product business case sound ?
Gate 3 opnes the gate to expensive product development. Cross-functional agreement that the product meets the previously approved consumer proposition: and business justification for proceeding to commercialisation. To proceed the score must exceed 65/130.
Strategic Fit & Importance
|  | 0 | 4 | 7 | 10
Is not aligned with business & innovation strategy | [5 empty] | Aligns well with Innovation Strategy
Limited or no impact on growth targets | [5 empty] | Significant impact on Growth targets
Market & Consumer opportunity assessment
|  | 0 | 4 | 7 | 10
Poor Insight | [5 empty] | Sizeable potential market with strong insight underpinning
Small Market, low growth, small profit pool | [5 empty] | Ability to penetratemarket
Daunting competition | [5 empty] | Weak competitive environment
Consumer proposition: Brand positioning & strategy
|  | 0 | 4 | 7 | 10
Provides the same benefits as competing products | [5 empty] | Highly differentiated benefits relative to competitors
Consumar and customer see little value in offer | [5 empty] | Consumer & customer see significant value
Negative feedback | [5 empty] | Very positive feedback
Organisatinal capability (Launch Plan)
|  | 0 | 4 | 7 | 10
Lack of clarity about how we will launch this new product | [5 empty] | Preliminary launch plan (sales & marketing) based on sound insight, and is clear and actionable
Probability of operations & technical success
|  | 0 | 4 | 7 | 10 | High. No technical or Operations gap. No new technology required. Starightforward ad attainable technical solution
Very large techincal gap
Very complex. Major hurdles and probably not achievable
Value creation: Financial and risk assessment
|  | 0 | 4 | 7 | 10
Low expected returns | [5 empty] | Signifcant financial returns
High levels of risk | [5 empty] | Manageable levels of risk
Total Score
Recommendation
Go | Stop |  |  |  |  | Recycle | Hold